## Legend
Glossary
XP | Extreme Programming
RUP | Rational Unified Process
DSDM | Dynamic Systems Development Method
FDD | Feature-Driven Development
LSD | Lean Software Development

## Key Characteristics
XP | SCRUM | RUP | DSDM | FDD | LSD
Lean Systems Society Credo
A team of 5 to 10 people working at one location with customer representation | Small, cross-functional teams working closely together in an open environment to produce incremental releases after 30-day sprints | full ALM approach (inception, elaboration, construction, and transition) | Development is a team effort, combining technical and business knowledge | develop and refine systems of substantial scope | Accept the human condition
frequent releasable builds delivering incremental functionality | Self-directed teams that are empowered to meet the objectives of each sprint | software development method and design best practices for almost all ALM disciplines | High quality necessitates fitness for purpose and technical robustness | develop based on domain object models in collaboration with domain experts | Accept that complexity & uncertainty are natural to knowledge work
requirements are grouped in stories representing a chunk of desired functionality | (Non-Technical) Scrum Master helps resolve impediments and reinforces application of SCRUM principles | projects are split up in multiple iterations | development is incremental |  | Work towards a better Economic Outcome
programmers work in pairs, following strict coding standards, and performing unit tests | Work is organized in Product Backlog, with priorities set each sprint | incremental in nature | resources are limited and must be spent on developing features relevant to the business |  | While enabling a better Sociological Outcome
requirements, architecture and design emerge through the project |  |  |  |  | Seek, embrace & question ideas from a wide range of disciplines
A values-based community enhances the speed & depth of positive change

## Principles & Values
XP | SCRUM | RUP | DSDM | FDD | LSD
Communication between programmers and between programmers and customers | Built-in stability through team empowerment | Attack major risks early and continuously | Active user involvement is imperative | Develop an Overall Mode | develop at reduced cost
Focus on simplicity. Code the simplest designs first. | Self-organizing project teams | Ensure you deliver value to the customer | Empowered teams | Build a Features List | develop with improved quality
Immediate feedback on development (within hours) | Overlapping development phases (design, build, test) | Stay focused on executable software | Frequent delivery of feaures | Plan by Feature | Reduced investment in elaborating requirements and documenting design
Courage: to write tests before, pick simplest solutions, get feedback | Multilearning by providing an environment for cross-polination of knowledge | Accomodate change early in the project | Fitness for business purpose is essential for acceptance of delivery |  | Develop in much smaller iterations with more frequent releases
Respect for the other team members | Subtle Control through daily meetings | Baseline an executable architecture early on | Iterative and incremental development is key to converge on an accurate delivery |  | increase cross-training with pair programming
Humanity: Software is written by people for people. Get engagement from people to get to innovative ways to solving problems. | Organization Transfer of Learning | Build your system with components with scalability and robustness in mind | All changes during development are reversible |  | Extensive developer testing with a focus on test automation
Reflection: Look back at what went well and what went wrong at regular intervals to improve future endeavors |  | Work together as a team, that is cross-functional and empowered | High-level requirements are the starting point for development |  | Collocate the team as much as feasible
Quality: Always ensure quality, and never make trade-offs, since scope is variable, and time and cost are fixed. |  | Make quality a way of life, not an afterthought. Testing should be integral to the project at every step of the way. | Integrated testing throughout hte entire application lifecycle |  | Continuous reflection and adaptation
Baby Steps: Make small incremental changes and upgrades during each sprint to achieve a big result at the end of several sprints. |  |  | Collaboration between all stakeholder is essential |  | Self-organizing, self-managing teams

## Core Practices
XP | SCRUM | RUP | DSDM | FDD | LSD
Sit Together as a team. | Small, cross-functional teams working closely together in an open environment to produce incremental releases after 30-day sprints | Develop iteratively | Time-boxing of iterations | Domain Object Modeling
All necessary skills for each iteration must be present as a whole team. | Self-directed teams that are empowered to meet the objectives of each sprint | Manage requirements | MoSCoW as a prioritization technique of business needs | Development by Feature
Informative Workspace: Visualize progress during the iteration. | (Non-Technical) Scrum Master helps resolve impediments and reinforces application of SCRUM principles | Use component architectures | Light-weight Modeling | Class (and Code) Ownership
Avoid less productive overtime, but try to achieve Energized Work. | Work is organized in Product Backlog, with priorities set each sprint | Model visually | Prototyping of the solution | Feature Teams as a collection of owners of related classes
Pair Programming |  | Continuously monitor quality | Continuous Testing throughout the entire lifecycle | Code Inspection by peers to assure quality
Iterations take a weekly cycle. |  | Verify change. Manage it through configuration and change management | Configuration Management to deal with code changes and refactoring | Regular Build Schedule
Large cycles (made up of smaller iterations) are planning in a quarterly cycle. |  |  |  | Configuration Management to deal with code changes and refactoring
Foresee some time contingency or slack in each iteration, usually in the form of nice-to-have features. |  |  |  | Reporting of Results and Progress
Automated builds should ten-minute builds, no longer.
Continuous Integration
Test-First Programming (applying TDD)
Incremental Design